## Change Log (hidden)
# | Strategic Area(s) | Requestor(s) Contact Name | Updated By | EDGE Update (As of MM/DD/YY) | Project Phase | Task ID | Information of Change(s)
1 | Finance | Henry Wang | Karla Goris (ACN) | 2019-07-31 | Design | CONF101 | Add new task
2 | Change Management | Jina Braynon | Karla Goris (ACN) | 2019-07-31 | Design | COMM1102 | Add new task
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217

## Instructions
Departmental/Office Activity Checklist - Instructions
Thoroughly review this instruction document before completing the County Department Readiness Checklist. The steps below outline how to complete each field in the template and defined available choices. Always use the dropdown menu when available.
Steps | Section | Column | Field | Instructions
1 | Departmental Activity Checklist | F | Task ID | An identifying alphanumeric associated with each task item
2 | Departmental Activity Checklist | G | Type (Task/Event) | An indicator if it’s a Task (action item) or an Event (Meeting, Planned occasion etc.)
3 | Departmental Activity Checklist | H | Project Release | Project Release (Rollout 1: Finance/Supply Chain, Rollout 2: HCM/Payroll, Rollout 3: Planning and Budgeting/Scorecard, Rollout 4: OBIA Finance/Supply Chain and Rollout 5: OBIA HCM)
4 | Departmental Activity Checklist | I | Project Phase | Identifier of EDGE Project Phase (Design, Build, Test, Deploy)
5 | Departmental Activity Checklist | J | Task Group | Responsible EDGE group associated with the task
6 | Departmental Activity Checklist | K | Task/Event Description | A brief description of action to be taken or event
7 | Departmental Activity Checklist | L | Activity/Task Owner(s) | County Department resource assigned to the task
8 | Departmental Activity Checklist | M | Required EDGE Project Submission (Y/N)? | Yes or No indicators if items should be submitted to the EDGE Project Team
9 | Departmental Activity Checklist | N | Specific Activity Start Date (MM/DD/YY) | Day, Month and Year dates for start date of task/event
10 | Departmental Activity Checklist | O | Specific Activity Due Date (MM/DD/YY) | Day, Month and Year dates for due date of task/event
11 | Departmental Activity Checklist | P | Task Deleted? (Y/N) | Yes or No indicators if task is no longer needed
12 | Notes | Q | Additional Task Update Comments | Comments, as necessary
13 | Departmental Activity Checklist | R | Task Criticality (Low, Medium, High) | High, Medium or Low of importance of task/event
14 | Departmental Activity Checklist | S | Applicable to all Departments? (Y/N) | Notation of task/event impact to all departments or specific departments
15 | Notes | T | If Answer is 'No' in column N, identify which department(s) | Comments, as necessary
16 | Departmental Activity Status | U | Task ID (Column F) | An identifying alphanumeric associated with each task item
17 | Departmental Activity Status | V | Task/Event Description (Column K) | A brief description of action to be taken or event
18 | Departmental Activity Status | W | Department Name | Drop-down list of department name
19 | Departmental Activity Status | X | Department Status | Department Status (Not Started, In Progress, Completed, At Risk)
20 | Departmental Activity Status | Y | Completed By (Name) | Name of Change Agent/Liaison which completed the task
21 | Departmental Activity Status | Z | Actual Completion Date (MM/DD/YY) | Day, Month and Year dates of completion
22 | Departmental Activity Status | AA | Department Status Comments | Comments, as necessary

## Departmental Activity Checklist
Change Management Office (CMO) Updates |  |  |  | Departmental/Office Activity Checklist | [15 empty] | Departmental/Office Activity Status
CMO Received from Change Agent (MM/DD/YY) | Reviewed (MM/DD/YY) | Approved (MM/DD/YY) | CMO Distribute Update (MM/DD/YY) | # | Task ID | Type (Task / Event) | Project Release | Project Phase | Task Group | Task/Event Description | Activity/Task Owner(s) | Required EDGE Project Submission? (Y/N) | Specific Activity Start Date (MM/DD/YY) | Specific Activity Due Date (MM/DD/YY) | Task Deleted? (Y/N) | Additional Task Update Comments | Task Criticality (Low, Medium, High) | Applicable to all Departments? (Y/N) | If Answer is 'No' in column N, identify which department(s) | Task ID (Column F) | Task/Event Description (Column K) | Department Name | Department Status | Completed By (Name) | Actual Completion Date (MM/DD/YY) | Department Status Comments
|  |  |  | 1 | CONF101 | Task | R1 - Finance/Supply Chain | Design | Configuration Management | Complete the EDGE Department ChartField Build Values Workbook | Finance Strategic Area Liaison(s) | Yes | 2019-07-31 | 2019-08-29 |  |  | High | Yes |  | CONF101 | Complete the EDGE Department ChartField Build Values Workbook |  | Not Started
|  |  |  | 2 | GENR101 | Task | R1 - Finance/Supply Chain | Design | General Readiness | Review the Department User Count spreadsheet. Provide an updated count on the number of Employees and Manager. | Change Agent(s) | Yes | 2019-07-31 | 2019-08-15 |  |  | Low | Yes |  | GENR101 | Review the Department User Count spreadsheet. Provide an updated count on the number of Employees and Manager. |  | Not Started
|  |  |  | 3 | GENR102 | Task | R1 - Finance/Supply Chain | Design | General Readiness | UPCOMING: Review Account List and Verify the information | Finance & Supply Chain Strategic Area Liaison(s) | Yes | TBD | TBD | [5 empty] | GENR102 | UPCOMING: Review Account List and Verify the information |  | Not Started
|  |  |  | 4 | CONF102 | Task | R1 - Finance/Supply Chain | Design | Configuration Management | UPCOMING: Complete EDGE Fund Chartfield | Finance Strategic Area Liaison(s) | Yes | TBD | TBD | [5 empty] | CONF102 | UPCOMING: Complete EDGE Fund Chartfield |  | Not Started
|  |  |  | 5 | CONF103 | Task | R1 - Finance/Supply Chain | Design | Configuration Management | UPCOMING: Provide Project values and activities | Finance Strategic Area Liaison(s) | Yes | TBD | TBD | [5 empty] | CONF103 | UPCOMING: Provide Project values and activities |  | Not Started
|  |  |  | 6 | CONF104 | Task | R1 - Finance/Supply Chain | Design | Configuration Management | UPCOMING: Confirm Interfaces | Finance Strategic Area Liaison(s) | Yes | TBD | TBD | [5 empty] | CONF104 | UPCOMING: Confirm Interfaces |  | Not Started
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123

## KEY (hidden)
Task Group | Prefix | Notes
General Readiness | GENR | TASK ID # is composed by TASK GROUP Prefix, Rollout Period, # on Spreadsheet.
Communications | COMM
Integrations / Interfaces | INTE
Configuration Management | CONF
Reporting | REPO
Data Cleansing / Conversion | DATA
Testing | TEST
Role Mapping | ROMA
Training | TRNG
Deployment Support | DEPL
Post Go-Live Support | POST
User Acceptance Training (UAT) | USER
Reporting Requirements | REQU

## Valid Values (DO NOT DELETE) (hidden)
Task | R1 - Finance/Supply Chain | Plan | General Readiness | Not Started | Yes | Change Agent(s) | Low | Animal Services
Event | 2: HCM/Budget | Analyze | Communications | In Progress | No | Finance Strategic Area Liaison(s) | Medium | Audit/Management Services
| On-going | Design | Integrations / Interfaces | Completed | N/A | Supply Chain Strategic Area Liaison(s) | High | Aviation
|  | Build | Configuration Management | At Risk |  | Technical Strategic Area Liaison(s) |  | Clerk of Courts
|  | Test | Reporting | N/A |  | Finance & Supply Chain Strategic Area Liaison(s) |  | Communications
|  | Deploy | Data Cleansing / Conversion |  |  | Strategic Area Liaison(s) |  | Community Action & Human Services
|  | Post Implementation | Testing |  |  |  |  | Corrections & Rehabilitation
|  | Monthly | Role Mapping |  |  |  |  | County Attorney's Office
|  | Quarterly | Training |  |  |  |  | Cultural Affairs
|  | Weekly | Deployment Support |  |  |  |  | Elections
|  | Bi-Weekly | Post Go-Live Support |  |  |  |  | Finance
|  |  | User Acceptance Training (UAT) |  |  |  |  | Fire/Rescue
|  |  | Reporting Requirements |  |  |  |  | Homeless Trust
Human Resources
Information Technology
Inspector General
Internal Services
Juvenile Services
Libraries
Management and Budget
Medical Examiner
Miami Dade Economic Advocacy Trust
Parks, Recreation, and Open Space
Police
Property Appraiser
Public Housing/Community Development
Regulatory & Economic Resources
Seaport
Solid Waste
Transportation & Public Works
Water & Sewer

## Example - EDGE Task List (hidden)
Department Task Information
# | Task ID | Type (Task / Event) | Project Release | Project Phase | Task Group | Task/Event Description (example strategies) | Activity / Task Owner(s) | Required EDGE Project Submission? (Y/N) | Specific Activity Start Date (MM/DD/YY) | Specific Activity Due Date (MM/DD/YY) | Task Deleted? (Y/N) | Additional Task Update Comments | Task Criticality (Low, Medium, High) | Applicable to all Departments? (Y/N) | If Answer is 'No' in column N, identify which department(s)
1 | CONF101 | Event | R1 - Finance/Supply Chain | Build | Configuration Management | Data requests for configuration will be communicated from the EDGE Project for the Technical Strategic Area Liaison(s) to complete. Some data request which will be used for testing will require a workshop to complete. | Technical Strategic Area Liaison(s) | Yes
2 | CONF102 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | After receiving the configuration requests, the Technical Strategic Area Liaison(s) will collect the necessary input to complete the data request and provide the department-defined values. | Technical Strategic Area Liaison(s) | No
3 | COMM103 | Task | R1 - Finance/Supply Chain | Build | Communications | Strategic Area Liaison(s) coordinates department discussions of the new Countywide future ("to-be") processes following the Business Process Workshops (BPW). Identify department-specific impacts to be included in department leadership updates, department communications, implementation of organizational changes, and department user training. | Strategic Area Liaison(s) | No
4 | CONF104 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Create Chart of Accounts mapping from legacy GL system to PeopleSoft Chart of Accounts | Functional Strategic Area Liaison(s) | No
5 | CONF105 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Chart of Account cross-walk defined by each department for each financial transaction conversion. | Technical Strategic Area Liaison(s) | No
6 | CONF106 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Update department applications for new Chart of Accounts. | Technical Strategic Area Liaison(s) | No
7 | CONF107 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Develop department process for cross-walking data on interfaces into/out of PeopleSoft to legacy Chart of Accounts. | Technical Strategic Area Liaison(s) | No
8 | CONF108 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Provide Customers data to the EDGE Project | Strategic Area Liaison(s) | No
9 | CONF109 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Prior to department submission of Chartfield workbooks, the Finance Strategic Area Liaison(s) will review and approve. If needed, the Finance Strategic Area Liaison(s) will provide the department with any updates that need to be made to the Chartfield Workbooks. | Finance Strategic Area Liaison(s) | Yes
10 | CONF110 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments will need to provide cardholder and default accounting strings for each Pcard at their department. | Change Agent(s) | Yes
11 | CONF111 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | All departments must review and update Location table workbook. This Countywide table will be used by Finance and Supply Chain teams and all County departments. | Technical Strategic Area Liaison(s) | Yes
12 | CONF112 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | After ChartField workbook has been reviewed, Change Agent(s) will publish the new Chart of Account values and crosswalks provided. Departments are to review and provide any updates before Chart of Account values and crosswalks are loaded into PeopleSoft. | Change Agent(s) | Yes
13 | CONF113 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | After the Chartfield workbooks have been submitted and loaded into PeopleSoft, the departments must validate the PeopleSoft chartfield values. | Strategic Area Liaison(s) | Yes
14 | CONF114 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define the default Return To Vendor (RTV) location. This will be used as the picking location when no MSL is defined on the RTV. Typically defined as location for rejected stock. | Supply Chain Strategic Area Liaison(s) | No
15 | CONF115 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to review Inventory Business unit list and update descriptions as needed and add additional Inventory Business Units where departments see fit. | Technical Strategic Area Liaison(s) | Yes
16 | CONF116 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define item groups and families that can be defined for an item to further categorize items outside of the NIGP code. | Supply Chain Strategic Area Liaison(s) | Yes
17 | CONF117 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define purchasing kits that will be utilized to issue several items with different quantities by selecting a single kit ID. | Technical Strategic Area Liaison(s) | Yes
18 | CONF118 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the Hazard Disposal codes that can be defined for an item using the workbook provided. | Technical Strategic Area Liaison(s) | Yes
19 | CONF119 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define the catalogs to be used by the department and the items associated to the catalog. This applies to only those items that will be loaded into the PeopleSoft. | Technical Strategic Area Liaison(s) | Yes
20 | CONF120 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define Par locations that will be utilized by your department (e.g. par location can represent a hospital cart where goods will be issued to and expensed immediately) | Technical Strategic Area Liaison(s) | Yes
21 | CONF121 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define all potential storage areas and the storage locations within an area for the warehouse. Do not define the item associated to the area/location. | Technical Strategic Area Liaison(s) | Yes
22 | CONF122 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the Role Title Definitions using the workbook provided. | Technical Strategic Area Liaison(s) | Yes
23 | CONF123 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the Credit Analyst Template using the workbook provided. | Technical Strategic Area Liaison(s) | Yes
24 | CONF124 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the Billing Specialist Template using the workbook provided. | Technical Strategic Area Liaison(s) | Yes
25 | CONF125 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the Collectors Template using the workbook provided. | Technical Strategic Area Liaison(s) | Yes
26 | CONF126 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the AR Specialist Template using the workbook provided. | Technical Strategic Area Liaison(s) | Yes
27 | CONF127 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | All departments must review and update Location table workbook. This Countywide table will be used by Finance and Supply Chain teams and all County departments. Also, the departments are to signify their Primary location. | Technical Strategic Area Liaison(s) | Yes
28 | CONF128 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the departments configuration values to be used in the Project Costing and Grants module. | Technical Strategic Area Liaison(s) | Yes
29 | CONF129 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to review the ChartField lists and submit requests for final changes to Chart of Accounts to include in Mock 1 and Testing | Technical Strategic Area Liaison(s) | Yes
30 | CONF130 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to review the ChartField lists and submit requests for final updates to Chart of Accounts to include in Mock 2 | Technical Strategic Area Liaison(s) | Yes
31 | CONF131 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to review the ChartField lists and submit requests for final updates to Chart of Accounts to include in User Acceptance Testing (UAT) | Technical Strategic Area Liaison(s) | Yes
32 | CONF132 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to review the ChartField lists and submit requests for final updates to Chart of Accounts to include in Mock 3 | Technical Strategic Area Liaison(s) | Yes
33 | CONF133 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define the Transaction accounting rules that will be associated to the different type of transactions performed by the departments from an inventory perspective (e.g. Issue, Putaway, Return, adjustment, etc.) | Technical Strategic Area Liaison(s) | Yes
34 | CONF134 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define the requisition defaults for requisitions that will be created via the replenishment process or backorder process (e.g. requestor, ship to, chartfields, etc..) | Technical Strategic Area Liaison(s) | Yes
35 | CONF135 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to define Return Material Authorization (RMA) chartfields. This represents the ChartField string that gets hit when goods are returned to the inventory warehouse. | Technical Strategic Area Liaison(s) | Yes
36 | CONF136 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to identify the Operating Expense Budgets roll up level they wish to use for budget structure where the identified chartfield is to be rolled up | Technical Strategic Area Liaison(s) | Yes
37 | CONF137 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to provide the rules that will be loaded into PeopleSoft to automate overdue charging for the departments. | Technical Strategic Area Liaison(s) | Yes
38 | CONF138 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to review and update the Appropriation chartfields of Description and Short Description fields. If they do not have any updates, no further action is required on the departments part. | Technical Strategic Area Liaison(s) | Yes
39 | CONF139 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Departments are to provide detailed information on the departments configuration values to be used in the Project Costing and Grants module. The values to be updated are the F&A GL Expense Accounts and Sponsored Program Office | Technical Strategic Area Liaison(s) | Yes
40 | CONF140 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Work with the Strategic Area Liaisons to identify the workbooks that impact their department. | Change Agent(s) | Yes
41 | CONF141 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to provide the information necessary for the Market Pay functionality. Information such as salary survey data will be loaded into the system to compare against organizational compensation levels. | Technical Strategic Area Liaison(s) | Yes
42 | CONF142 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to collect the values for the Charge Codes and Distribution Codes. There is a separate workbook for each. | Technical Strategic Area Liaison(s) | Yes
43 | CONF143 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Specific departments are needed to confirm which deposit accounts will be processing payments to be applied against open receivables issued from PeopleSoft, so the accounts can be built in Cash Management | Technical Strategic Area Liaison(s) | Yes
44 | CONF144 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to list the frequently used comments that are noted on procurement transactions to be pre-defined in PeopleSoft. | Technical Strategic Area Liaison(s) | Yes
45 | CONF145 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to create Program Attributes if they choose. These ChartFields will be loaded into PeopleSoft for their department use for Go-Live. | Technical Strategic Area Liaison(s) | Yes
46 | CONF146 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to determine and request if any changes or additional Chartfield values are to be available in Production. No action is required if no changes or additional values are needed. | Technical Strategic Area Liaison(s) | Yes
47 | CONF147 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to create department operating budgets using the workbook provided and to update, if required, the operating budget definitions. | Technical Strategic Area Liaison(s) | Yes
48 | CONF148 | Task | R1 - Finance/Supply Chain | Build | Configuration Management | Department are to provide the desired statistical accounts in allocations. Statistical account values are stored in the Account ChartField. They are used to track statistical data such as sq. footage or head count, and are used to capture statistical amounts only, not monetary amounts. | Technical Strategic Area Liaison(s) | Yes
49 | DATA149 | Task | R1 - Finance/Supply Chain | Build | Data Cleansing / Conversion | The EDGE Technical Team will colloborate in defining the Technical File Format and Standards for Extracted Data. | Technical Strategic Area Liaison(s) | No
50 | DATA150 | Task | R1 - Finance/Supply Chain | Build | Data Cleansing / Conversion | Converting legacy system owners will be responsible for designing the methods for extracting data from their current systems and meeting the requirements for data file layouts and extraction rules, as well as new validation queries and reports as necessary. Expected output for this phase should include completed documentation for data extract logic. | Technical Strategic Area Liaison(s) | No
51 | DATA151 | Task | R1 - Finance/Supply Chain | Build | Data Cleansing / Conversion | Create extract of data from legacy system per the requirements from the EDGE Application Development Team | Technical Strategic Area Liaison(s) | Yes
52 | DATA152 | Task | R1 - Finance/Supply Chain | Build | Data Cleansing / Conversion | Change Agent(s) (and other liaisons as needed) will meet with Strategic Area Liaison(s) to report status on Conversions and Interface. This status will be used to drive scorecard status/color for Conversions. | Change Agent(s) | Yes
53 | GENR153 | Task | R1 - Finance/Supply Chain | Build | General Readiness | Technical Strategic Area Liaison(s) validates that the end-user workstations at the departments meet the requirements for hardware and software. | Technical Strategic Area Liaison(s) | Yes
54 | GENR154 | Event | R1 - Finance/Supply Chain | Build | General Readiness | Strategic Area Liaison(s) will conduct department discussions of the new processes following the Business Process Workshops (BPWs) and complete the BPW impact assessment for the department process areas. The Following will need to be addressed: - Assess new reports and identify additional critical operational reports - Assess process changes and plan for implementing process changes within the department - Identify and escalate department business scenarios that are not able to be met within the new enterprise design | Strategic Area Liaison(s) | Yes
55 | GENR155 | Event | R1 - Finance/Supply Chain | Build | General Readiness | Strategic Area Liaison(s) coordinates the creation of new and update existing business process documentation at the department to reflect the new business processes. Status is reviewed with the EDGE Change Management team and tracked using the Department Readiness Checklist. | Strategic Area Liaison(s) | No
56 | GENR156 | Task | R1 - Finance/Supply Chain | Build | General Readiness | Identify necessary organization changes and plan for implementing organization changes. | Change Agent(s) | No
57 | GENR157 | Task | R1 - Finance/Supply Chain | Build | General Readiness | Change Agent(s) determine the department demographics for R1, Survey 2 and R2, Survey 1 | Change Agent(s) | Yes
58 | GENR158 | Task | R1 - Finance/Supply Chain | Build | General Readiness | Completed tasks required to ensure the release of Readiness Survey 2. | Change Agent(s) | No
59 | GENR159 | Task | R1 - Finance/Supply Chain | Build | General Readiness | Review and share department’s own Change Readiness Survey 2 results with department Leadership. | Change Agent(s) | Yes
60 | INTE160 | Task | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | Identify & develop specific department Systems Integrations and Processes (needed in 3 month period between the first Fin/Proc release and the release of HCM) | Change Agent(s) | No
61 | INTE161 | Task | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | (If required) Complete Data Cleansing | Technical Strategic Area Liaison(s) | No
62 | INTE162 | Event | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | Receive Technical File Format and Standards for Interfaced Data | Technical Strategic Area Liaison(s) | Yes
63 | INTE163 | Task | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | Develop and Unit Test the department Interface Programs | Technical Strategic Area Liaison(s) | No
64 | INTE164 | Event | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | Strategic Area Liaisons confirms with the EDGE Project Integration Testing participants. | Strategic Area Liaison(s) | No
65 | INTE165 | Event | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | Change Agent(s) confirms department contacts to support Integration Testing | Change Agent(s) | No
66 | INTE166 | Task | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | Converting legacy system owners will be responsible for delivering the Integration extract file. | Technical Strategic Area Liaison(s) | Yes
67 | INTE167 | Task | R1 - Finance/Supply Chain | Build | Integrations / Interfaces | Converting legacy system owners must provide the Integration extract file. | Technical Strategic Area Liaison(s) | Yes
68 | REPO168 | Event | R1 - Finance/Supply Chain | Build | Reporting Requirements | Assess countywide "to-be" process and identify any department-specific reporting needs | Strategic Area Liaison(s) | No
69 | REPO169 | Event | R1 - Finance/Supply Chain | Build | Reporting Requirements | Strategic Area Liaisons works with department General Ledger functional team to determine the preferred nVision report configuration settings. | Strategic Area Liaison(s) | No
70 | REPO170 | Task | R1 - Finance/Supply Chain | Build | Reporting Requirements | Change Agents will review the report inventory and identify any missing reports with their department. Departments will be responsible for closing reporting gaps via their internal business intelligence or legacy applications, utilization of the EDGE support organization reporting approach (i.e. building queries and having them migrated to production), or submitting report requests to the EDGE project. | Change Agent(s) | Yes
71 | ROMA171 | Event | R1 - Finance/Supply Chain | Build | Role Mapping | Change Agent(s) coordinates and conducts ongoing change conversations at the department between managers and supervisors and department end users of the EDGE System. | Change Agent(s) | No
72 | ROMA172 | Task | R1 - Finance/Supply Chain | Build | Role Mapping | Change Agent(s) provides the EDGE Project with contact information (name, email, phone) and Job Classifications of all anticipated end-users. | Change Agent(s) | Yes
73 | ROMA173 | Event | R1 - Finance/Supply Chain | Build | Role Mapping | Change Agent(s) coordinates the submissions of end-user role assignments to the EDGE Project. | Change Agent(s) | No
74 | ROMA174 | Event | R1 - Finance/Supply Chain | Build | Role Mapping | Change Agent(s) & Strategic Area Liaison(s) manage the process to assign the roles to end-users and complete the role mapping spreadsheet. | Change Agent(s) | No
75 | ROMA175 | Task | R1 - Finance/Supply Chain | Build | Role Mapping | In preparation for training delivery, departments are required to identify the number of users in each department role by reviewing the EDGE roles and descriptions, then determining the number of system users that will perform that function, by role. Optionally, the departments will also determine each individual user who will perform that function. | Change Agent(s) | Yes
76 | TRNG176 | Task | R1 - Finance/Supply Chain | Build | Training | Technical Strategic Area Liaison validates department training locations can connect to the county's network and URLs. | Technical Strategic Area Liaison(s) | No
77 | TRNG177 | Event | R1 - Finance/Supply Chain | Build | Training | Select department participants that will complete Train the Trainer program and serve as trainers to department end users. | Change Agent(s) & Strategic Area Liaison(s) | Yes
78 | DEPL178 | Task | R1 - Finance/Supply Chain | Deploy | Deployment Support | Strategic Area Liaison(s) coordinates department participation in the EDGE Project Go-Live activities, validating conversion processes and data for go live. Coordinate communications on go-live conversion activities and participate in go-live conversion validation. | Strategic Area Liaison(s) | No
79 | DEPL179 | Task | R1 - Finance/Supply Chain | Deploy | Deployment Support | Technical Strategic Area Liaison(s) coordinates department participation in the EDGE Project Go-Live activities. Departments conduct transition planning activities to finish FY19-FY20 transactions outside of the EDGE System and begin the EDGE System processing on 10/1/2020. | Strategic Area Liaison(s) | No
80 | DEPL180 | Event | R1 - Finance/Supply Chain | Deploy | Deployment Support | Technical Strategic Area Liaison(s) coordinates department participation in the EDGE Project Dry Run, a walkthrough of Go-Live activities and processes. | Technical Strategic Area Liaison(s) | No
81 | DEPL181 | Event | R1 - Finance/Supply Chain | Deploy | Deployment Support | Strategic Area Liaison(s) coordinates department participation in workshop to discuss cutover activities and timeline for department system retirements or transitions. | Strategic Area Liaison(s) | No
82 | DEPL182 | Event | R1 - Finance/Supply Chain | Deploy | Deployment Support | Review cutover validation activities and associated department tasks. | Strategic Area Liaison(s) | No
83 | INTE183 | Event | R1 - Finance/Supply Chain | Deploy | Integrations / Interfaces | Prepare for deployment of new interfaces and decommissioning of Legacy Interfaces (if no longer required) | Technical Strategic Area Liaison(s) | No
84 | CONF184 | Task | R1 - Finance/Supply Chain | Design | Configuration Management | The Functional Strategic Area Liaison(s) communicates data request for department information. Each department completes the template provided and provide values back to the EDGE team per the request instructions. | Functional Strategic Area Liaison(s) | Yes
85 | CONF185 | Task | R1 - Finance/Supply Chain | Design | Configuration Management | Complete the inventory questionnaire and return to the Change Agent(s). | Strategic Area Liaison(s) | Yes
86 | CONF186 | Task | R1 - Finance/Supply Chain | Design | Configuration Management | Update current Inventory Processes and Systems for Enterprise To-Be Inventory Processes (specific departments only). | Strategic Area Liaison(s) | No
87 | DATA187 | Event | R1 - Finance/Supply Chain | Design | Data Cleansing / Conversion | Data mapping identifies the fields in the PeopleSoft tables, the corresponding field or location of data in the legacy system(s), and any business rules that must be applied to the data in the field to convert it to a PeopleSoft valid value. | Technical Strategic Area Liaison(s) | No
88 | DATA188 | Task | R1 - Finance/Supply Chain | Design | Data Cleansing / Conversion | The Development team will play a coordinating role in data cleansing by providing feedback on cleansing needs, as well as proposed solutions to data quality issues. The Technical Strategic Area Liaison(s) are responsible for making any physical changes to source data for the purpose of data cleansing. | Technical Strategic Area Liaison(s) | No
89 | DATA189 | Task | R1 - Finance/Supply Chain | Design | Data Cleansing / Conversion | Receive and understand the EDGE data conversion requirements and collaborate in defining data mapping. | Technical Strategic Area Liaison(s) | No
90 | GENR190 | Task | R1 - Finance/Supply Chain | Design | General Readiness | Prepare department-specific readiness checklist for department activities with actions, resources, dates. | Change Agent(s) | Yes
91 | GENR191 | Task | R1 - Finance/Supply Chain | Design | General Readiness | Technical Strategic Area Liaison(s) coordinates analysis of department systems with systems owners, business/IT owners, and the EDGE Project. | Technical Strategic Area Liaison(s) | No
92 | GENR192 | Task | R1 - Finance/Supply Chain | Design | General Readiness | Technical Strategic Area Liaison(s) reviews system disposition recommendations with the EDGE Project. The goal is to confirm department System Impacts. | Technical Strategic Area Liaison(s) | Yes
93 | GENR193 | Task | R1 - Finance/Supply Chain | Design | General Readiness | Change Agent(s) & Strategic Area Liaison(s) coordinates the review of existing business process documentation to prepare the department for the new countywide business processes. | Change Agent(s) & Strategic Area Liaison(s) | No
94 | GENR194 | Event | R1 - Finance/Supply Chain | Design | General Readiness | Department participants attend enterprise Business Process Workshops. | Strategic Area Liaison(s) | Yes
95 | GENR195 | Event | R1 - Finance/Supply Chain | Design | General Readiness | Change Agent(s) coordinates department discussions of the new processes following the Business Process Workshops (BPWs) and completes the Business Process impact assessment for the department. | Change Agent(s) | Yes
96 | GENR196 | Task | R1 - Finance/Supply Chain | Design | General Readiness | Review and share department’s own Change Readiness Survey results with department Leadership | Change Agent(s) | Yes
97 | GENR197 | Task | R1 - Finance/Supply Chain | Design | General Readiness | After the BPW have been completed, departments will complete the Department Change Management Impact Analysis which will describe the business process changes their department will be affected by. | Change Agent(s) | Yes
98 | INTE198 | Task | R1 - Finance/Supply Chain | Design | Integrations / Interfaces | Functional Strategic Area Liaison(s) coordinates department review of legacy system analysis recommendation. | Functional Strategic Area Liaison(s) | No
99 | INTE199 | Event | R1 - Finance/Supply Chain | Design | Integrations / Interfaces | Receive the integration requirements (Functional Specs information) | Functional Strategic Area Liaison(s) | Yes
100 | INTE1100 | Task | R1 - Finance/Supply Chain | Design | Integrations / Interfaces | Complete System data mapping | Technical Strategic Area Liaison(s) | No
101 | ROMA1101 | Task | R1 - Finance/Supply Chain | Design | Role Mapping | Change Agent(s) identify department participants for the Role Mapping kick-off. | Change Agent(s) | Yes
102 | COMM1102 | Task | All Rollouts | Monthly | Communications | Change Agent(s) monitors and reports on their Department's status of the Readiness Checklist to the EDGE Project. | Change Agent(s) | Yes
103 | COMM1103 | Task | All Rollouts | Monthly | Communications | Create and manage a plan for sharing information internally and externally | Change Agent(s) | Yes
104 | GENR1104 | Event | All Rollouts | Monthly | General Readiness | Change Agents (only) participate in monthly meeting with All Change Agents. | Change Agent(s) | No
105 | GENR1105 | Task | All Rollouts | Monthly | General Readiness | Raise issues and risks to the EDGE Change Management Team. Work together to track and resolve. Escalate through County leadership and the EDGE governance as appropriate. | Change Agent(s) | No
106 | GENR1106 | Task | All Rollouts | Quarterly | General Readiness | Review the Department Change Agent Network roles and responsibilities provided. | Change Agent(s) & Strategic Area Liaison(s) | Yes
107 | GENR1107 | Task | R1 - Finance/Supply Chain | Quarterly | General Readiness | Update department-specific readiness checklist for department activities with actions, resources, dates for the quarter and with specific department activities. | Change Agent(s) | No
108 | TRNG1108 | Event | All Rollouts | Quarterly | Training | Change Agent(s) participates in a regular discussions with the EDGE Project on awareness messages regarding Train the Trainer and End-User Training Delivery | Change Agent(s) | No
109 | DATA1109 | Task | R1 - Finance/Supply Chain | Test | Data Cleansing / Conversion | Ensure Mock Conversion results from PeopleSoft match legacy data extracts that were submitted to the EDGE Application Development Team via reconciliation reports, SQL queries, or online transactions | Technical Strategic Area Liaison(s) | Yes
110 | INTE1110 | Task | R1 - Finance/Supply Chain | Test | Integrations / Interfaces | Submit department Test Files and Participate in Integration Testing | Strategic Area Liaison(s) | Yes
111 | INTE1111 | Task | R1 - Finance/Supply Chain | Test | Integrations / Interfaces | Validate interfaced data during integration test | Technical Strategic Area Liaison(s) | No
112 | INTE1112 | Task | R1 - Finance/Supply Chain | Test | Integrations / Interfaces | Create date extract from legacy system per the requirements from the EDGE Application Development Team. Integration testing will allow the testing of interface processes and asses the progress of the data clean-up efforts. Ensure Integration Test results from PeopleSoft match legacy data extracts that were submitted to EDGE. | Technical Strategic Area Liaison(s) | No
113 | ROMA1113 | Task | R1 - Finance/Supply Chain | Test | Role Mapping | Department and Change Agents are to review and refresh the end-user level role assignments to the EDGE Project before Go-Live. | Change Agent(s) | Yes
114 | TRNG1114 | Task | R1 - Finance/Supply Chain | Test | Training | Change Agent(s) coordinates registration of all end-users at the department for End-User Training. End-User Training for department end users is identified based on their assigned end-user roles. | Change Agent(s) | No
115 | TRNG1115 | Task | R1 - Finance/Supply Chain | Test | Training | Change Agent(s) are to monitor department participation in the End-User Training. The EDGE Training team will provide Change Agent(s) with recurring training reports. | Change Agent(s) | No
116 | TRNG1116 | Event | R1 - Finance/Supply Chain | Test | Training | Change Agent(s) manages department end user participation in training support activities. Department end users attend Future State Simulations to practice transactions associated with their assigned the end-user roles. | Change Agent(s) | No
117 | TRNG1117 | Event | R1 - Finance/Supply Chain | Test | Training | Change Agent(s) attends a formal kickoff designed to introduce how the training program will unfold, their responsibilities and next steps. | Change Agent(s) | No
118 | TRNG1118 | Event | R1 - Finance/Supply Chain | Test | Training | Change Agent(s) registers department end users for participation in training support activities. | Change Agent(s) | No
119 | USER1119 | Task | R1 - Finance/Supply Chain | Test | User Acceptance Training (UAT) | Change Agent(s) provides the EDGE Project with contact information (name, email, phone) for UAT participants by the Enterprise Strategic area. UAT involves a small group of department business users in the Project testing effort to verify the systme performs as designed. UAT participants help review test scenarios, participate in a UAT kickoff, and attend process-specific UAT sessions. | Change Agent(s) | Yes
120 | USER1120 | Event | R1 - Finance/Supply Chain | Test | User Acceptance Training (UAT) | Change Agent(s) manages department review of UAT scenarios, and the identification of additional scenarios to be added to UAT or unscripted testing sessions. | Change Agent(s) | No
121 | USER1121 | Event | R1 - Finance/Supply Chain | Test | User Acceptance Training (UAT) | Change Agent(s) coordinates department's UAT participants attendance in UAT Kickoff, which prepares department end users for UAT processes, e.g. how to run a test script, how to log a bug or defect, and how to capture UAT results. UAT involves department business users in the Project testing effort to verify the EDGE Project performs as designed. | Change Agent(s) | No
122 | USER1122 | Event | R1 - Finance/Supply Chain | Test | User Acceptance Training (UAT) | Change Agent(s) manages department participation in UAT training sessions. UAT Training provides UAT participants with basic the system navigation training. UAT involves department business users in the Project testing effort to verify the EDGE Project performs as designed. | Change Agent(s) | No
123 | USER1123 | Event | R1 - Finance/Supply Chain | Test | User Acceptance Training (UAT) | Departments are to provide unique department business scenarios and data sets for the testing. | Strategic Area Liaison(s) | No
Note on G93: Goris, Karla: Clarification on Who the Systems Owners are
Note on G94: Goris, Karla: Functional SAL